## Slide 1: Finding MIMO
Weekly Meeting: Week 7
Kate Bowers, Kristopher Jung, Samuel Spillane

## Slide 2: Project Goals
Model receiver-side CEs to determine the best way to decode received signals
  Choose equalization algorithm and parameters
  Choose channel estimation technique
Optimize parameters for the best Bit Error Rate (BER), Power Gain, or throughput

## Slide 3: Progress and challenges
Kate worked on MIMO Watterson baseline
  Modular implementation for testing equalizer designs in parallel
  Validity checking of existing models using Rayleigh and AWGN channels
Kris worked on equalizers and Genetic Algorithm.
  Still have issues on equalizers.
  Training stepsize/# forward taps/ # feedback taps
  Population = 50
  Generations = 100

## Slide 4: Progress and challenges Contd.
Sam worked on Q-Learning.
  Developed method for exhaustive action space transversal
  Even with advanced programming techniques(backtracking, dynamic programming, branch and bound) the process of creating an exhaustive action space for multiple variables still uses too much memory for sufficiently large variable ranges.
  Therefore, I am finalizing a model for to reduce the number of parameters for each q-learning session and therefore increasing the available action space.

## Slide 5: Progress and challenges Contd.
Overall discussion of design specifications of CE
  Testing design with Q-Learning as a possible final design, will revisit this week
Determination of variables to be controlled by the CE
  Step size
  Feedback/feed-forward taps
  Forgetting factor
  Equalizers

## Slide 6: End-game research design.

## Slide 7: Roadmap
Week 7
  Finalize q-learning and genetic algorithm.
  Synchronize all works.
  Fix issues in equalizers together.
Week 8-10
  Other tasks
  Research paper writing
  Research poster/video for presentation (Are we supposed to do a poster or video?)

## Slide 8: Questions?