## Slide 1: Finding MIMO
Weekly Meeting: Week 8
Kate Bowers, Kristopher Jung, Samuel Spillane

## Slide 2: Project Goals
Model receiver-side CEs to determine the best way to decode received signals
  Choose equalization algorithm and parameters √
  Choose channel estimation technique √
Optimize parameters for the best Bit Error Rate (BER), Power Gain, or throughput √
Create a working MIMO implementation with equalization
Create a high-quality research paper that conveys the novelty of our project

## Slide 3: Progress and challenges
Completely redid and generalized (M x N) MIMO model
  Original strategy not representative of Watterson model
    Stdchan compatible with SISO
  Immediate improvement in performance of equalizers
Wasted time trying to fix equalizers when channel model was creating the issues
  Matlab equalizers also has lot of issues dealing with MIMO systems.
    Implemented ZF/MMSE/MLD by hand.
    Started implementing DFE by hand
Completed visualization block to format simulation results

## Slide 4: Progress and challenges Contd.
Sam finished Q-learning algorithm and began the writing process.
  Q-Learning
    Works on a continuous cycle, always optimizing all parameters for each equalizer. Always finds global optima, while being more efficient than previous versions.
  Writing
    Began reading papers to acquire examples of research writing and began plotting the abstract.

## Slide 5: ZF/MMSE/MLD
3 x 2 MIMO Watterson
BPSK
100 iteration per SNR
BER vs SNR
50 symbols each transmitter per iteration for the sake of time.

## Slide 6: End-game research design.

## Slide 7: Roadmap
Week 8-10
  Finish DFE equalizers
  Integrate all CEs
  Finalize project tasks
  Research paper writing
  Research poster/video for presentation

## Slide 8: Questions?